## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Two
Enter Company Name in cell B2. | Complete this template by replacing the bracketed text with the relevant information in each row. Also, in the relevant columns, be sure to enter start and end dates and experiment with entering progress percentages to create the Gantt chart bars.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  | 2025-02-05
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | 14 |  |  | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-05-05 to 2025-06-29
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PROGRESS | START | END | DAYS | time axis 2025-05-05 to 2025-06-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Security Awareness Training Implementation |  | 2025-02-01 | 2025-03-01 | 29
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Develop security awareness training materials | 100% | 2025-02-01 | 2025-02-15 | 15
| Schedule employee training sessions | 100% | 2025-02-16 | 2025-02-25 | 10 | bar: 2025-05-18 to 2025-05-27
| Conduct training and collect feedback | 100% | 2025-02-26 | 2025-03-01 | 4
| Milestone: Completion of employee training | 100% | 2025-03-01 | 2025-03-01 | bar: 2025-05-31
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Security Policy and Incident Response Plan |  | 2025-03-02 | 2025-04-01 | 31
| Draft formal security policies | 100% | 2025-03-02 | 2025-03-15 | 14
| Create structured incident response plan | 75% | 2025-03-16 | 2025-03-25
| Conduct policy review and approval | 30% | 2025-03-26 | 2025-04-01 | 7
| Milestone: Approval of security policies and incident response plan |  | 2025-04-01 | 2025-04-01
| Network Segmentation and Hardware Upgrade |  | 2025-04-02 | 2025-05-01
| Assess current network segmentation gaps | 45% | 2025-04-02 | 2025-04-15 | 14
| Procure and install new hardware | 50% | 2025-04-16 | 2025-04-25 | 10
| Test and validate network changes | 0% | 2025-04-26 | 2025-05-01 | 6
Milestone: Implementation of network segmentation
| Security Audits and Final Testing |  | 2025-05-02 | 2025-06-30
| Conduct security audits and vulnerability assessments | 10% | 2025-05-02 | 2025-05-15
| Review compliance with new policies | 5% | 2025-05-16 | 2025-05-25
| Final testing and approval | 1% | 2025-05-26 | 2025-06-15 | 21
| Milestone: Completion of security audit and project closure | 0% | 2025-06-16 | 2025-06-16 | 1
| Milestone: Completion of Multi-Factor Authentication (MFA) Rollout | 0% | 2025-06-17 | 2025-07-01
Adapted from a template by TeamGantt (2019), https://www.teamgantt.com/

## Resource Allocation
Complete this template by entering the relevant information in each row.
Task | Resource | Rationale
Develop security awareness training materials | Software Engineers Team Lead | Responsible for creating digital training content and ensuring usability.
Schedule employee training sessions | Project Manager | Ensures alignment with department schedules and stakeholder expectations.
Conduct training and collect feedback | HR Department | Directly engages employees in training and gathers feedback for improvement.
Milestone: Completion of employee training | Stakeholders | Confirms that employees have completed required training.
Draft formal security policies | Project Manager | Ensures policies align with organizational security needs and compliance requirements.
Create structured incident response plan | Software Engineers Team Lead | Develops technical incident response procedures and automation workflows.
Conduct policy review and approval | Stakeholders | Provide final approval and ensure policies meet business objectives.
Milestone: Approval of security policies and incident response plan | Stakeholders | Final endorsement of security policy implementation.
Assess current network segmentation gaps | Hardware Engineers Team Lead | Evaluates infrastructure to identify areas needing segmentation improvements.
Procure and install new hardware | Contractor | Handles physical installation and ensures proper configuration.
Test and validate network changes | IT Department | Conducts functionality tests and ensures secure network integration.
Milestone: Implementation of network segmentation | Stakeholders | Ensures segmentation meets security and operational requirements.
Conduct security audits and vulnerability assessments | Project Manager | Oversees audits and ensures all vulnerabilities are documented and addressed.
Review compliance with new policies | HR & IT Departments | Ensures employees and technical infrastructure comply with new security policies.
Final testing and approval | Stakeholders | Conducts final review and officially closes the project.
Milestone: Completion of security audit and project closure | Stakeholders | Final review of security measures before project closeout.
Milestone: Completion of Multi-Factor Authentication (MFA) Rollout | IT Department | Ensures full implementation and integration of MFA across systems.